## Feuil1
APIS AND UI DATA MODELS COMPARISON
Feature | Methods | Endpoints | Difference with frontend
Therapy | POST: all these apis should be checked | /therapies | in api data model patID property should be a number not a patient object
in therapy form Therapy duration in days, weeks and months are missing in api model
The api does not work, it gives a 500 error, constraint violations on medicalId
|  | /therapies/from-row | It does'nt work also
|  | /therapies/from-rows | It does'nt work also
|  | /therapies/meds-out-of-stock | It gives a 500 error, null pointer exception
|  | /therapies/replace | It does'nt work also
| DELETE | /therapies/{code_patient} | IT IS OK
| GET | /therapies/{code_patient} | IT IS OK
Booking | Not availables | Not availables | In forms with have category of services, service and booking date, also for each service we want to have two arrays: list of non availables days, and the list of barely Available days
Examinations (Triage) | POST | /examinations | Examinations api data model is missing the following properties: diuresis vol 24H, respiratory_rate, hgt, diuresis, bowel, auscultation. The triage form is missing the property pex_note which is present in api data model. But the API works
| GET | /examinations/byPatientId/{patId} | It is OK
| GET | /examinations/fromLastPatientExamination/{id} | It is OK but when the id is not found it return 500 error (null pointer exception)
| GET | /examinations/defaultPatientExamination | It is OK
| GET | /examinations/lastByPatientId/{patId} | It is OK
| GET | /examinations/lastNByPatId | It is OK
| GET | /examinations/{id} | It is OK
| PUT | /examinations/{id} | It is OK
OPD | POST | /opds | It is not working. OPD form is missing these properties: next Visit Date, referral From, referral To, newPatient
| GET | /opds/ProgYear/{year} | It is OK
| GET | /opds/check/progyear | It is OK
| GET | /opds/patient/{pcode} | It is OK